## Issues
| Issue Tracker | [11 empty] | Freiter
ID | Name | Depend On | Type | Use Cases | Priority | Problem Description | Solution Description | Code Blocks Affected | Effort Estimation | Additional Information | Status | Editor
0 | Advanced Process Models |  | RESTRUCTURE |  |  | process_models_advanced -> model_learning | RESTRUCTURE | Model | 0 |  | DONE | Freiter
1 | Factory Planner mergen |  | NEW FEATURE |  |  |  | Mergen | FactoryPlanner | 1 |  | DONE | Freiter
2 | DynamicAttributes |  | PERFORMANCE | for a large change history |  | performance issue if many entries available | usage of lambda architecture behavior - crossover should be implemented | Model | 4 |  | DONE | Freiter
3 | RESTRUCTURE Codebase |  | USABILITY | Better understanding of the code structure |  | Diffcult the find the right access points into the code | better structure | All | 1 |  | DONE | Freiter
4 | Get Input Parameters of each DT Object (elegant) |  | NEW FEATURE | - Data Integration (for the mapping to the object) |  | attributes needed for the object are currently derived from the init annotations (elegance is a problem) | get_input_parameters() - method of each DTObject | Model; DataIntegration | 3 | need tests (changes should throw an error) | DONE | Freiter
5 | Export mergen |  | NEW FEATURE |  |  |  | Mergen | Model; Export | 2 |  | DONE | Freiter
6 | Introduction of lib management |  | ADMINISTRATION |  |  |  | Poetry |  | 1 |  | OPEN
7 | Introduction of Tests |  | ADMINISTRATION |  |  | Development difficult because of bugs if something is changed … | PyTest |  | 4 |  | IN PROGRESS
8 | Agent Architecture |  | NEW FEATURE | [5 empty] | 5 |  | OPEN
9 | Scenario | 7 | SHOW/ TEST | Show Case |  |  |  |  | 1 |  | OPEN
10 | Show input parameters on the Editor |  | RESTRUCTURE/ NEW FEATURE | - Frontend (display the following parameters) |  | How do I know, which attributes a object has? - should be dynamic based on the digtal twin |  | Model; FactoryPlanner |  |  | OPEN
11 | EntitiesTuple |  | USABILITY | ProcessExecution parts_involved/ resources_used |  | List of tuple management should be not a duplicate (clean code required); get_list of entities often used - performance | Introduction of a class that manage the list of tuples … | Model; maybe other areas | 2 |  | IN PROGRESS | Freiter
12 | Factory Planner Extension |  | NEW FEATURE |  |  | Which parameters should be shown on the Frontend?/ How to access to them … | Mapping and Extensions | Model; FactoryPlanner | 2 |  | OPEN
13 | Feature Combination Rules |  | NEW FEATURE |  |  | SalesOrder generation with combination dependent features | Feature Combination Rules | Model; SalesGenerator | 2 |  | OPEN
14 | Digital Twin Persistence |  | NEW FEATURE | Save the history |  | The current solution is not suitable for high volume data | DataBase | persistence | 4 |  | OPEN
15 | Concept for DT Versioning |  | NEW FEATURE | Worker leaves the company, new machine etc. entering the DT |  | The DTM does not say, if an DT object/ attribute "EXIST", "IS DESTROYED", "CREATED ON", etc. | Object/ attribute history? |  | 5 | Meeting with Christian and Adrian required | OPEN